## Final_as on 4thMarch_cost
New Requirement - Delivery Timelines
Sl No | Module | Requirment | SDL Comments | Efforts (in days) | Escalon Comments | Date of Delievery
1 | E-Evaluaiton | E-Evaluation history report | Extra customisation - shall be charged at actuals | 2 | Ok |  | Completed
2 | Dashbaord | Module wise dashboard | New Version will be updated with module-wise dashboard | Free | ok | 19th March 2019
3 | Leave | In Leave module, instead of 12 EL and 6 CL/SL, we require 18 Els only. | Extra customisation - Shall be done free of cost. Require exact employee leave balance | Free along with new dashboard | Ok | 19th March 2019
4 | Attendance | Freeze option to lock that particular month attendance related details | Extra customisation - shall be charged at actuals | 7 | ok | 5th April, 2019
5 |  | Shift -wise holiday list |  |  |  | 5th April, 2019
6 | Leave | Freeze option to lock that particular month leave related details |  |  |  | 21st March 2019
7 | E-Resignation | Need detailed growth path history for resigned employees | New Version will be updated with module-wise dashboard | Free along with new dashboard | ok | 23rd March 2019 | working
8 | Leave | Split Leave Reports | Will be customised without cost | Free along with new dashboard | Ok | 23rd March 2019
9 | Leave | Automatic transition from Probationary to confirmed employee in which leave balance and everything else gets automatically transitted | Extra customisation - shall be charged at actuals | 4 | Ok | 30th March 2019 | completed
10 | Leave | Report of history of leaves available to the user as well to reporting manager | Extra customisation - shall be charged at actuals | 3 | Waiting for cost | 30th March 2019 | completed
11 | Attendance | Need an option to view comp off report similar to leave report | . | 6 Discounted Days - 3 | As discussed, 3 days efforts to be calcualted | 29th March 2019 | completed
12 |  | Comp off Approval should go to virtual head(Head Of Department) |  |  |  |  | completed
13 |  | Holiday work Approval should go to virtual head(Head Of Department) |  |  |  |  | completed
14 |  | Need an option to view holiday work off report similar to leave report |  |  |  |  | completed
15 | Payroll | History of Resigned employee details like payslip or any payroll related data | Extra customisation - shall be charged at actuals | 2 | Ok | 5th April, 2019 | working
16 | On Boarding & Employee Module | Mulitple Choose file option for Upload | Can you specify the list of documents so that we will update the timeframe. | 5 | lets wait for cost/will provide data in second week of March so we can skip it for now | Awaiting for Data. | completed
17 | Email Notification | Comp off/Holiday work notifications are not configured. | Please provide the extra notification for each of the modules. Extra customisation and shall be charged at actuals | Included in Point 7 | Ok | Upon receiving notification list, the delivery date will be finalised | completed
|  |  | TOTAL | 31 Days
NOTE: Efforts charged at the rate of Rs. 3000 / manday, but as an exception to Escalon, we shall charge @ Rs.2500/man day keeping in mind our long term professional relationship