## Sheet1
MOJO - HRIS - HRMS TASKS TIME SCHEDULE
SL No. | Module | Sub module/Submenu | Pages/Sections | Description | Required Time | Developer status
1 | Employee | Add Employee | 1.Add New employee using dialog box | 1.Design layout for 'add employee' module page | ---------------- | Completed
2.Create View page and design the page for profile information with necessary fileds.
3.Add profile information using dialog box with necessary fileds.
4.Create Model with necessary fileds, Interface, services, mapping
5.Create controller and writing logic for required methods(post, put, get, delete)
6.Create the table through migration.
|  |  | 2.Profile tab | Perform the below tasks for sections of : 1.Personal Information | -------------------- | Completed
2.Emergency Contact
3.Work Information(Primary)
4.Work Information(Secondary)
5.Skill set
6.Education Informations
7.Experience
8.Current Work Information
1 .Create View pages and design the pages with necessary fileds.
2.Add required information using dialog box with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | 3.Policy Mapping tab | 1 .Create View pages and design the pages with necessary fileds. | 13/05/2024 | In progress
2.Add required information using dialog box with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | 4.Bank & Statutory | Perform the below tasks for sections of : 1.Salary Basics | -------------------- | Completed
2.PF Information
3.ESI Information
4.Provident Fund/Gratuity Nominations
5.ESI/Medical Insurance Nomination
1 .Create View pages and design the pages with necessary fileds.
2.Add required information using dialog box with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | 5.Overseas | Perform the below tasks for sections of : 1.Foreign Citizenship | ------------------------- | Completed
2.Foreign Sojourns
3.Visa Available
4.International Driving License
1 .Create View pages and design the pages with necessary fileds.
2.Add required information using dialog box with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | 6.Salary | Perform the below tasks for sections of : 1.Annual Salary | 2024-05-16 | Need to assign
2.Deductions
1 .Create View pages and design the pages with necessary fileds.
2.Create grids to display salary details and deductions information.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | 7.Projects | Information needed to implement this page | --------------------- | -----------------
|  |  | 8.Health | Information needed to implement this page | --------------------- | ------------------
|  |  | 9.Document | Perform the below tasks for sections of : 1.Photo Id Proof | ---------------------- | Completed
2.Address Proof
3.Other Documents
1 .Create View pages and design the pages with necessary fileds.
2.Add required information using dialog box with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Active Employees | Active Employees | Perform the below tasks for sections of : 1.Employee List | ----------------------- | Completed
1 .Create View pages and design the pages with necessary fileds.
2.Display the employee list in cards with necessary fileds.
3.Providing options for edit and delete the employee.
4.Redirecting the page to edit employee.
|  | Inactive Employees | Inactive Employees | Perform the below tasks for sections of : 1.Employee List | ----------------------- | Completed
1.Display the Inactive employee list in cards with necessary fileds.
2.Providing the option to active the employee.
|  | Approver Configuration | Approver Configuration | Perform the below tasks for sections of : 1.Approver Configuration | 18/05/2024 | Need to do(Kumar)
2.Approver Information
3.Other Documents
1.Need to complete the assign roles.
2 .Create View pages with grid using necessary fileds.
3.Create dialog box to add required information with necessary fileds.
4.Create Model with necessary fileds, Interface, services, mapping
5.Create controller and writing logic for required methods(post, put, get, delete)
6.Create the table through migration.
|  | Transfer | Transfer | Perform the below tasks for sections of : 1.Add Transfer | 24/05/2024 | Need to do(Kumar)
2.View transfer
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Resignation | Resignation | Perform the below tasks for sections of : 1.Add Reasignation | 2024-05-29 | Need to do(Kumar)
2.View Resignation
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Termination | Termination | Perform the below tasks for sections of : 1.Add Termination | 2024-05-29 | Need to do(Kumar)
2.View/Edit Termination
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
2 | Leave | Leave policy | Create Leave policy | Perform the below tasks for sections of : 1.Add Leave policy | 2024-06-04 | Need to assign
2.View/Edit Leave Policy
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Leave master | Create Leave master | Perform the below tasks for sections of : 1.Add Leave master
|  |  |  | 2.View/Edit Leave master | 2024-06-06 | Need to assign
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Leave rule | Create Leave rule | Perform the below tasks for sections of : 1.Add Leave rule | 2024-06-06 | Need to assign
2.View/Edit Leave rule
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Apply Leave | Create Apply leave | Perform the below tasks for sections of : 1.Apply leave
|  |  |  | 2.View/Edit apply leave | 2024-06-10 | Need to assign
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Leave status | Leave status | Perform the below tasks for sections of : 1.View leave status | 2024-06-11 | Need to assign
1 .Create View pages with grid using necessary fileds.
3.Create Interface, services, mapping
4.Create controller and writing logic for required methods( get)
|  | Approve Leaves | Approve Leaves | Perform the below tasks for sections of : 1.Approve leave | 2024-06-12 | Need to assign
2.View/Edit approve leave
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
3 | Attendance | Attendance Master | Create shift Master | Perform the below tasks for sections of : 1.Add shift master | 2024-06-15 | Need to assign
2.View/Edit shift master
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | Create attendance rule | Perform the below tasks for sections of : 1.Add attendance rule | 2024-06-15 | Need to assign
2.View/Edit attendance rule
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | Machine Code & IP address | Perform the below tasks for sections of : 1.Create machine code & IP address | 2024-06-15 | Need to assign
2.View/Edit machine code & IP address
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | Download attendance log | Perform the below tasks for sections of : 1.Create download attendance log | 2024-06-17 | Need to assign
2.View/Edit download attendance log
1 .Create View pages with grid using necessary fileds.
2.Create Interface, services, mapping
3.Create controller and writing logic for required methods(get)
4 | Payroll | Payroll master | Add/view payhead | Perform the below tasks for sections of : 1.Create payhead | 2024-06-18 | Need to assign
2.View payhead
1 .Create View pages with grid using necessary fileds.
2.Create Interface, services, mapping
3.Create controller and writing logic for required methods(get)
|  |  | Tax payers details | Perform the below tasks for sections of : 1.Create tax payers details | 2024-06-21 | Need to assign
2.View/Edit tax payers details
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  |  | Create allowance | Perform the below tasks for sections of : 1.Create tax payers details | 2024-06-21 | Need to assign
2.View/Edit tax payers details
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Approver structure | Create pay strudcture | Perform the below tasks for sections of : 1.Create pay structure | 2024-06-21 | Need to assign
2.View/Edit pay structure
1 .Create View pages with grid using necessary fileds.
2.Create page to add required information with necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods(post, put, get, delete)
5.Create the table through migration.
|  | Salary Report | Pay slip | Perform the below tasks for sections of : 1.Create pay sslip | 2024-06-22 | Need to assign
2.View pay slip
1 .Create View pages with grid using necessary fileds.
3.Create Model with necessary fileds, Interface, services, mapping
4.Create controller and writing logic for required methods( get )